## Sheet1
Schedule
Team Meetings
Due Dates
Date | Objective | Description
2019-01-24 | Team Meet and Greet | Team will hold initial meeting and assign responibilities to each team member.
2019-01-29 | Team Meeting (Project Start) | Team will determine team name and game design and goals.
2019-01-31 | Team Meeting (SA/RFP) | Team Banana will start discussion for it's system analysis and RFP project.
2019-02-01 | Team Meeting (SA/RFP) | Team Banana will determine responsibilities for each team member for the system analysis and RFP project and set goals for completion.
2019-02-04 | Team Meeting (SA/RFP) | Team Banana will discuss progression on it's system analysis and RFP project.
2019-02-06 | Team Meeting (SA/RFP) | Team Banana will review and complete it's system analysis and RFP and have it ready to present.
2019-02-07 | SA/RFP Presentation | Team Banana will present it's system analysis and RFP.
2019-02-08 | Team Meeting (Repository and Diagrams) | Team Banana will review it's peformance for it's SA and RFP presentation. Team Banana will discuss it's code repository and team member responsibilities for the team diagrams (Class Diagram, Sequence Diagram, and Gantt Chart).
2019-02-14 | Status Report 1 (Repository and Diagrams) | Code repository and diagrams (Class Diagram, Sequence Diagram, and Gantt Chart) will be completed for Team Banana.
2019-02-15 | Team Meeting (Skeleton Code) | Team Banana will disuss team members responsibilities to start coding for the Debugger game.
2019-02-21 | Status Report 2 (Skeleton Code) | Team members skeleton code and a makefile will be complete. All team members code must compile and run "something".
2019-02-22 | Team Meeting (Testing) | Team Banana will discuss progression for the Debugger game and team member responsibilities to test the code.
2019-02-28 | Status Report 3 (Testing) | All team member's test plans will be completed and merged together.
2019-03-01 | Team Meeting (Game Progression) | Team Banana will discuss progression of game devolpment and team member responsibilities.
2019-03-08 | Team Meeting (Game Progression and Second Gantt Chart) | Team Banana will discuss progression of game deveolpment and team member responsibilities for the second team Gantt Chart.
2019-03-21 | Status Report 4 (Game Progression and Second Gantt Chart) | Game should look nearly complete. Second team Gantt Chart should be completed.
2019-03-22 | Team Meeting (Game Completion 1 and Coding Standards) | Team Banana will discuss progression of game development, Gantt Chart updates, and coding standards.
2019-03-28 | Status Report 5 (Game Completion 1 and Coding Standards) | First trial run of completed Debugger game. Coding standards will be set. The team Gantt Chart will be updated.
2019-03-29 | Team Meeting (Game Completion 2 and User's Manual) | Team Banana will discuss progression of game development, Gantt Chart updates, and the user's manual.
2019-04-04 | Status Report 5 (Game Completion 2 and User's Manual) | Second trial run of completed Debugger game. User's manual will be finished. The team Gantt Chart will be updated.
2019-04-05 | Team Meeting (Game Presentation) | Team Banana will discuss progression of game development and team member responsibilities for the final presentation of the Debugger game.
2019-05-01 | Team Meeting (Game Presentation) | Team Banana will prepare for the final presentation of the Debugger game.
2019-05-02 | Final Presentation | Team Banana will hold it's final presentation for the Debugger game.
2019-05-05 | Grades | Dr. BC will assign each team member and the team as a whole an "A" for the final grade.