## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Ben | 1500 | 1275 | 225 | 0 | 0 | 0 | 1000 | 400 | 600 | 500 | 875 | -375
Luis | 1000 | 350 | 650 | 0 | 0 | 0 | 1000 | 350 | 650 | 0 | 0 | 0
Josh | 1800 | 950 | 850 | 0 | 0 | 0 | 1000 | 400 | 600 | 800 | 550 | 250
Joel | 1600 | 1000 | 600 | 0 | 0 | 0 | 1000 | 400 | 600 | 600 | 600 | 0
Blakely | 1000 | 400 | 600 | 0 | 0 | 0 | 1000 | 400 | 600 | 0 | 0 | 0
Nate | 1000 | 250 | 750 | 0 | 0 | 0 | 1000 | 250 | 750 | 0 | 0 | 0
Total | 7900 | 4225 | 3675 | 0 | 0 | 0 | 5000 | 1800 | 3200 | 1400 | 1150 | 250

## Gantt
| predicted time(hrs) | time spent(hrs) | key |  | completed |  |  | this week |  |  | planned
Ben |  |  | hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
totals | 0 | 0
Luis
totals | 0 | 0
Josh
totals | 0 | 0
Joel
totals | 0 | 0
Blakely
totals | 0 | 0
Nate
totals | 0 | 0
group totals (hrs) | 0 | 0
group totals ($) | 0 | 0

## Meetings
| Date | 2019-01-24 | 2019-01-29 | 2019-01-31 | 2019-02-01 | 2019-02-06 | TBD | TBD | TBD | TBD | TBD
| Purpose | First Meeting | Team Meeting | Team Meeting | Team Meeting | TBD | TBD | TBD | TBD | TBD | TBD
| Hours | 1.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0
Ben | 4 | ü | ü | ü | ü | ü
Luis | 3.5 | ü |  | ü | ü | ü
Josh | 4 | ü | ü | ü | ü | ü
Joel | 4 | ü | ü | ü | ü | ü
Blakely | 4 | ü | ü | ü | ü | ü
Nate | 2.5 |  | ü | ü | ü | ü
Total | 15.5 | 6 | 1.5 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Ben | Individual schedule
| RFP – part 6 | 1 | 0.75
| Champion | 3 | 6
| Presentation | 1 | 2
| Subtotal | 5 | 8.75
Luis | Individual schedule
RFP
Champion
Presentation
| Subtotal | 0 | 0
Josh | Individual schedule
| RFP | 2 | 1.5
| Champion | 4 | 3
| Presentation | 2 | 1
| Subtotal | 8 | 5.5
Joel | Individual schedule
RFP
Champion
Presentation
| Subtotal | 0 | 0
Blakely | Individual schedule
| RFP | 1.5 | 1.5
| Champion | 3 | 3
| Presentation | 1.5 | 1.5
| Subtotal | 6 | 6
Nate | Individual schedule
RFP
Champion
Presentation
| Subtotal | 0 | 0
| Total | 19 | 20.25